## Sprint Backlog 2
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | PRIORITY | STATUS | DAY 0 | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a teen, I can use the app on my mobile device, so that it's accessible on the go | 1 |  | HIGH | Completed
Add approriate bootstrap commands | 1 | Matthew, Euan, Sem, Laura, Jamie, Eddie |  |  |  | 1
As an older person, I want the icons on the homepage to be bigger, so that I can immediately see what each item is. | 2 |  | HIGH | Completed
Make the image for each item bigger than the header text | 2 | Matthew |  |  |  | 2
As a colour-blind person, I want events on the map to be represented by sustainable dundee petals, so that I can differentiate between my location and event locations | 3 |  | HIGH | Completed
Change blue dots to sustainable dundee petals | 3 | Matthew |  |  |  | 3
As a member of the public, I should see the address of all events selected on the map, so that I could find the event easily | 5 |  | HIGH | Completed
Update database format | 1 | Sem |  |  |  |  | 1
Insert new data into database | 3 | Sem |  |  |  |  | 3
Add new data to map page | 1 | Sem |  |  |  |  | 1
As a user, I want to be able to register for the site so that I can use the site functionality. | 8 |  | HIGH | Completed
Add registration page | 4 | Sem |  |  |  |  | 4
Take away normal users' ability to edit items | 4 | Sem | [7 empty] | 4
As a member of the public, I want to be able to change my password so that my account is more secure. | 3 |  | HIGH | Completed
add change password page | 1 | Sem |  |  |  | 1
push the change to the database | 2 | Sem |  |  |  | 2
As a teen, I can check into a location through social media , so that I can share my experiences | 5 |  | HIGH | Completed
Add a button to check in (via social media) | 2 | Laura |  |  |  | 2
Generate a prepopulated tweet text | 3 | Laura |  |  |  |  | 3
As a teen, I want to be able to check in to a location through social media on the map, so that I don't need to go to a goal each time. | 2 |  | HIGH | Completed
able to check in on map | 2 | Sem | [6 empty] | 2
As a member of the public, I want to be able to see news about sustainability so that I could be more informed | 3 |  | HIGH | Completed
Integration with Sustainable Dundee twitter's page | 3 | Laura | [5 empty] | 3
As a teen, I should be able to check into a location through the website. | 8 |  | HIGH | Completed
Modify database to add check in counter | 3 | Sem | [6 empty] | 3
Add check in button to map events | 1 | Sem | [7 empty] | 1
Add check in button to single events page | 1 | Sem | [7 empty] | 1
display activity locations to a user | 1 | Matthew, Euan, Jamie |  |  |  | 1
let a user to check in into a specific event | 2 | Sem | [5 empty] | 2
As a teen, I should be able to check a leaderboard that shows how many events I have been to compared to my friends | 8 |  | HIGH | Completed
create leaderboard | 5 | Sem, Euan | [5 empty] | 5
go through the code to check if everything's compatible with the updated users table | 3 | Sem | [6 empty] | 3
As a teen, I should be able to add friends on the website after registering | 8 |  | HIGH | Completed
Add page to add friends on website | 4 | Euan, Jamie |  |  |  |  | 4
Implement notification feature for friend requests | 2 | Euan, Jamie |  |  |  |  | 2
Check if relationship already exists | 2 | Euan, Jamie |  |  |  |  | 2
As a teen, I should be able to see a friends list on the website | 5 |  | HIGH | Completed
Modify database to include friends | 2 | Sem |  |  |  |  | 2
Show friends on list | 3 | Euan, Jamie |  |  |  |  | 3
As an eco-activist, I want to be able to suggest things to be added to the list of events by putting into a holding thing so that it can be approved by admin and added to the website. | 8 |  | HIGH | Completed
Allow users to suggest events | 3 | Sem |  |  |  |  | 3
Add database table to hold suggested events | 2 | Sem |  |  |  |  | 2
Allow admin to approve or delete suggested events | 3 | Sem | [5 empty] | 3
As a member of the public, I can see data from the UN (i.e. dataset of recycling points in Dundee), so that I can use it to be more sustainable | 8 |  | MEDIUM | Completed
parsing data from online json file | 2 | Laura | [6 empty] | 2
adding recycling points on a map | 2 | Laura | [6 empty] | 2
adding appropriate markers | 2 | Laura | [7 empty] | 2
filtering points based on recycled items | 2 | Laura | [7 empty] | 2
As an event organiser, I want to have a ‘tour’ of sustainable venues shown on a map that are close together . | 8 |  | MEDIUM | Completed
Implement direction mapping | 5 | Matthew, Eddie | [7 empty] | 5
Add 'event organiser' users | 1 | Matthew, Eddie | [5 empty] | 1
Create tour database table | 2 | Matthew, Jamie, Eddie | [5 empty] | 2
TOTAL | 85 |  |  |  |  | 12 | 30 | 16 | 12 | 15 | 0
For burndown graph |  |  |  |  | 85 | 73 | 43 | 27 | 15 | 0 | 0

## GOALS in Dundee
UNITED NATIONS SUSTAINABLE DEVELOPMENT GOALS - DUNDEE
UN Sustainable Development Goal | About the Goal | Things to do | Examples in Dundee | Useful Information | Website | POSTCODE
GOAL 1: NO POVERTY | End Poverty in all its forms everywhere. | Find a charity to support Donate what you don’t use to local charities or those in need | Dundee Bairns | Dundee Bairns is a charity working to benefit children in Dundee, addressing inequality in basic needs such as food and clothing. | https://dundeebairns.org/ | DD4 0DX
|  |  | Dundee Fighting for Fairness | The group is a voice for people in poverty in Dundee. | https://www.dundeefightingforfairness.co.uk/ | DD3 0AX
|  |  | Positive Steps Partnership | The charity provides supported accommodation services for vulnerable adults | https://positivesteps.org.uk/ | DD2 1DX
|  |  | FareShare Dundee | Provides support to homeless and vulnerable individuals and offers training and volunteering opportunities. One of their projects - Transform Furniture - is a community based project that works towards overcoming poverty by providing quality reusable furniture and electrical household items to disadvantaged local groups, and training and employment opportunities for local people having difficulties in finding a job whilst reducing the amount of household goods that end up in landfill. | https://www.transformcommunity.org.uk/food-poverty https://www.transformcommunity.org.uk/transform-furniture | DD1 5AZ
GOAL 2: ZERO HUNGER | End hunger, achieve food security and improved nutrition and promote sustainable agriculture | Buy local and in-season food. Try growing some of your own food Donlt waste food Buy "funny fruit" many fruits and vegetables are thrown out because their size, shape, or color are not “right”. Buying these perfectly good funny fruit, utilizes food that might otherwise go to waste. Consume less meat, eat more plant based. | Dundee Community Fridge (Gate Church Carbon Saving Project) | The Community Fridge at Gate Church is a communal place where surplus food is shared, by local businesses and individuals. The community fridge helps to cut food waste, build bonds within the community and re-distribute good quality food. Although the focus is on food waste, the Community Fridge also helps to reduce food poverty in Dundee. | https://www.gatechurch.co.uk/carbonsavingproject | DD1 4JA
|  |  | Dundee and Angus Foodbank | The Dundee and Angus Foodbank provide emergency food parcels for those in need and support people in crisis. It is part of a nationwide network of foodbanks, supported by The Trussell Trust, working to combat poverty and hunger across the UK. Locations both in Dundee and Angus. | https://dundeeandangus.foodbank.org.uk/ | DD2 3QN
|  |  | Taught by Muhammad | Taught By Muhammad is an outreach project aimed at building an understanding between Muslims and the wider community. The project also helps tackle social injustices within Dundee. They have several projects including curry kitchens where they cook for the homeless, a foodbank and schools outreach. *Potential for presentations in schools* | www.taughtbymuhammad.com | DD1 5HZ
|  |  | FareShare Dundee | FareShare Dundee collects/receives surplus quality food. The food is distributed to community organisations providing residential and day services for disadvantaged groups of people in Dundee, Perth & Kinross and Angus. | https://www.transformcommunity.org.uk/food-poverty | PH1 5PA
GOAL 3: GOOD HEALTH AND WELLBEING | Ensure healthy lives and promote well-being for all at all ages | Get vaccinated Donate Blood Walk! It’s good for the mind, body and environment. Take regular exercise, find a sport or activity you enjoy. Take care of your mental health. Meditate, talk to friends and family, and seek professional help. Research and development (work in Dundee) | Embark Dundee | Ride On operates the e-bike sharing services in Dundee. The e-bikes provide a sustainable and affordable mobility solution for moving around the city. | https://rideondundee.com/ | DD1 4BX
|  |  | Ancrum Outdoor Centre | The Ancrum Centre offers taster sessions, days out, skills development courses and coaching awards for people of all ages and abilities from the Dundee and wider Tayside region. Includes watersports, winter sports, cycling, climbing, hillwalking, first aid, team building and a group events. | https://www.ancrum.com/ | DD2 2HZ
|  |  | Aspire Programme Dundee | ASPIRE Dundee is a community engagement programme that uses performing arts across the curriculum to increase pupils’ health and wellbeing, self-confidence, self-esteem, learning and skills development. | https://education.gov.scot/improvement/practice-exemplars/aspire-programme-dundee/ | DD1 1QE
|  |  | Dundee Cycle Hub | The Dundee and Angus Cycle Hubs encourage people to lead healthier lives and reduce short car journeys and C02 emissions through cycling and recycling. They provide Bikeability training, bike hire, servicing and repairs and bike recycling. | https://www.anguscyclehub.org/dundee-cycle-hub | DD1 4EZ
GOAL 4: QUALITY EDUCATION | Ensure inclusive and equitable quality education and promote lifelong learning opportunities for all | Donate used books and resources to schools and kids groups | Charity shop across Dundee (for donating) | Red Cross, Shelter, Barnardo's, British Heart Foundation (amongst others) |  | Red Cross - DD1 1RG, DD2 1AU, DD2 1SW Shelter - DD1 1PN Barnardo's - DD1 1SP, DD3 7SE, DD4 7PU British Heart Foundation - DD1 2DB, DD1 2AZ, DD2 3BX
|  |  | Central Library |  | http://www.leisureandculturedundee.com/library/central-library-wellgate | DD1 1DB
GOAL 5:GENDER EQUALITY | Achieve gender equality and empower all women and girls | Voice your support for equal pay for equal work. Be aware of geneder sterotypes Stand up against harrassment | Soroptimists Dundee | The Soroptimists are a group of women working together to improve the lives of women and girls locally in Dundee, nationally and internationally. | https://www.facebook.com/soroptimistclubdundee/
|  |  | international Women's Day - 8th March | Event/campaign | https://www.internationalwomensday.com/
GOAL 6: CLEAN WATER AND SANITATION | Ensure availability and sustainable management of water and sanitation for all | Awareness campaigns Don't overuse water Organise a clean up project for rivers and beaches | Scottish Water | St Leonard Park Regeneration - Scottish Water, NatureScot and SEPA are working with Dundee City Council to develop and improve the way storm water is managed and reduce flood risk in the St Mary's area of Dundee. Water mains investment - Dundee Laird Street. 1km of new water main was installed to improve the water network serving Dundee's Laird Street. | https://www.scottishwater.co.uk/in-your-area/investments-in-your-area/st-marys-drainage | DD3 9HD
GOAL 7: AFFORDABLE AND CLEAN ENERGY | Ensure access to affordable, reliable, sustainable and modern energy for all | Switch off your appliances at the socket. Turn off the lights when you’re not using them. Buy rechargable electronics Don’t use multiple devices at the same time. Be mindful about this and only several devices when absolutely necessary. | MSIP | Michelin Scotland Innovation Parc - a world class innovation parc in Dundee for sustainable mobility and decarbonisation. *Potential events and opportunities to visit in the future.* | https://www.msipdundee.com/ | DD4 8UQ
|  |  | MVV Environment Baldovie - Energy from Waste | Energy from waste facility - may be able to offer tours/ open days. Opportunity to learn about biomass/ energy from waste | https://www.mvv.de/en/about-us/group-of-companies/mvv-umwelt/subsidiaries/mvv-environment-ltd/baldovie-efw-chp-facility-dundee | DD4 0NS
|  |  | Princes Street Charging Hub | EV charging hub with solar canopies. Potential to visit? | https://www.drivedundeeelectric.co.uk/princes-street | DD4 6AD
|  |  | Queen Street Charging Hub | EV charging hub with solar canopies. Potential to visit? | https://www.drivedundeeelectric.co.uk/queen-street | DD5 2HG
|  |  | Multi Storey car parks (MSPs) | Green Market, Olympia and Gellatly Street MSP's all have EV charging points. These sites encourage commuters to charge during the day and nearby residents to charge their EV at night. | https://www.drivedundeeelectric.co.uk/multi-storey-car-parks | DD1 1EX DD1 3DY
GOAL 8: DECENT WORK AND ECONOMIC GROWTH (Green economy, sustainable tourism) | Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all | Invite people with experience in a certain field to create a mentoring group that will help young people better prepare for their future jobs. Be a conscious consumer - if something is cheap is it likely to be hurting people or the planet in some way. Buy from local producers Support local economic growth by choosing to buy from local businesses | Dundee Science Centre | Events, activities, learning opportunities | https://www.dundeesciencecentre.org.uk/?gclid=Cj0KCQiAip-PBhDVARIsAPP2xc0DfaEICTubJ8ejpkqhdEUrRjuNVk7r55nA6MCzeyq6QCMv1sn3BygaAic7EALw_wcB | DD1 4QB
|  |  | V&A Dundee | Scotland's first design museum. Significant economic impact bringing £21 million to the Dundee economy in the first 12 months of opening and the creation of jobs across Scotland. | https://www.vam.ac.uk/info/plan-your-visit?gclid=Cj0KCQiAip-PBhDVARIsAPP2xc3B7pQ89FIbBCDg_D1rhdVo0TAsXx5JaqZz7rV1osUKhugv279otSwaAuRAEALw_wcB | DD1 4EZ
|  |  | Local independent businesses around Dundee | City Centre and Perth Road - hubs for local shops Refill Shops - Birchwood Emporium, The Little Green Larder, Love Your Planet | https://dundeedirectory.co.uk/earth-day-2021-dundee-shops/ | Dundee Dairy Co - DD3 8AS The Little Green Larder - DD2 1AE Birchwood Food Emporium - DD1 3EQ Love Your Planet - DD5 2AN
|  |  | Elevator | Elevator works across Dundee, Angus and Perth, providing practical help, advice and support to business across all sectors, whatever stage they’re at. *potential to do a workshop with schools?* | https://www.elevatoruk.com/business-support/dundee/ | DD1 5EN
GOAL 9: INDUSTRY, INNOVATION AND INFRASTRUCTURE | Build resilient infrastructure, promote inclusive and sustainable industrialization and foster innovation | Learn about innovation in your city, how to get involved, career opportunities in innovation, research and development. Make use of sustainable transport infrastructure. | MSIP | Michelin Scotland Innovation Parc - world class innovation parc in Dundee for sustainable mobility and decarbonisation. | https://www.msipdundee.com/ | DD4 8UQ
|  |  | MVV | Energy from waste facility in Dundee. *potential to visit at a later date* | https://www.mvv.de/en/about-us/group-of-companies/mvv-umwelt/subsidiaries/mvv-environment-ltd/baldovie-efw-chp-facility-dundee | DD4 0NS
|  |  | The MILL/ Urban Foresight | Mobility Innovation Living Lab, Dundee. The MILL is transforming Dundee ito a real-world test and experimentation environment for innovative mobility solutions. They provide expert support to large and small businesses. Including access to funding, infrastructure and end-users. *potential for school visits/workshops* | https://themill.scot/ | DD1 3EJ
|  |  | Danu Robotics | Robotics company with a robotic system for sorting recycling moving to MSIP. | https://danurobotics.com/ | DD4 8UQ
|  |  | S5GConnect Dundee | S5GConnect Dundee is opening a range of support, facilities and opportunities for businesses of all sizes to test and develop new 5G applications and services. *Find out more* | https://scotland5gcentre.org/s5gconnect/s5gconnect-dundee/ https://www.scotsman.com/business/dundee-selected-as-home-city-for-new-5g-innovation-hub-3174106 | DD1 1QE
|  |  | Dundee Esports Arena |  |  | DD1 3RT
|  |  | Dundee Eden Project |  |  | DD1 3RT
|  |  | Dundee Science Centre | Events, activities, learning opportunities | https://www.dundeesciencecentre.org.uk/?gclid=Cj0KCQiAip-PBhDVARIsAPP2xc0DfaEICTubJ8ejpkqhdEUrRjuNVk7r55nA6MCzeyq6QCMv1sn3BygaAic7EALw_wcB | DD1 4QB
|  |  | Dundee's Waterfront | Regeneration of Dundee City Waterfront. 30 year long project. (Visit and learn about the history, how the transformational changes have postivley impacted the city.) | https://www.dundeewaterfront.com/ | DD1 3AZ
|  |  | V&A Dundee | Scotland's first design museum. Significant economic impact bringing £21 million to the Dundee economy in the first 12 months of opening and the creation of jobs across Scotland. | https://www.vam.ac.uk/info/plan-your-visit?gclid=Cj0KCQiAip-PBhDVARIsAPP2xc3B7pQ89FIbBCDg_D1rhdVo0TAsXx5JaqZz7rV1osUKhugv279otSwaAuRAEALw_wcB | DD1 4EZ
|  |  | University of Dundee | One of the UK's leading universities, internationally recognised for its expertise across a range of disciplines . | https://www.dundee.ac.uk/ | DD1 4HN
GOAL 10: REDUCED INEQUALITY | Reduce inequality within and among countries | Rasie your voice against any type of discrimination. Support migrants and refugees in your community. | One World Centre Dundee | One World Centre promotes global justice and equality through education by supporting teachers, schools and community groups in Angus, Dundee, Fife and Perth & Kinross to engage in Global Citizenship through Professional Learning. | https://oneworldcentre.org.uk/ | DD1 1QE
GOAL 11: SUSTAINABLE CITIES AND COMMUNITIES (Incl. Sustainable Transport) | Make cities and human settlements inclusive, safe, resilient and sustainable | Shop locally. Supporting local businesses keeps people employed and circulates money back in to the local community. Travel sustainably - bike, walk or take public transport. Take care of public spaces. Organise clean ups, plant trees, renovate. | Embark Dundee | Ride On operates the e-bike sharing services in Dundee. The e-bikes provide a sustainable and affordable mobility solution for moving around the city. | https://rideondundee.com/ | DD1 4BX
|  |  | Dundee Cycle Hub | The Dundee and Angus Cycle Hubs encourage people to lead healthier lives and reduce short car journeys and C02 emissions through cycling and recycling. They provide Bikeability training, bike hire, servicing and repairs and bike recycling. | https://www.anguscyclehub.org/dundee-cycle-hub | DD1 4EZ
|  |  | Local independent businesses around Dundee | There are lots you can visit and support around Dundee! (this section can include a range of shops/businesses etc. Would be great to highlight refill shops, repair shops etc that contribute to a Circular Economy) | https://www.list.co.uk/places/independent-shops/location:Dundee(56.4631,-2.9796)/ https://www.dundeecity.gov.uk/service-area/city-development/planning-and-economic-development/independent-shops https://www.lovedundeelocal.co.uk/locations | Aitken's -> DD1 4JG, Aitken's -> DD1 4BE, Time Lifestyle Boutique -> DD1 1SL, Dundee Delights -> DD5 3EJ, Faerie Tree -> DD2 2JA, Gidi Grill -> DD1 3JA, Granada Cafe & Bakery -> DD2 4DD, The Selkie -> DD1 3DJ, The Butcher the Baker -> DD1 5JH | Local shops
|  |  | Electric Buses | Xplore Dundee, Stage Coach Buses, Ember. *Potential to visit? See charging?* | https://www.xploredundee.com/MissionZero https://www.stagecoachbus.com/promos-and-offers/east-scotland/route-20-and-21 | DD1 2AP
|  |  | Broughty Ferry and Monifieth Active Travel Improvements | Dundee City Council and Angus Council are working together to improve the National Cycle Network Route 1 between Broughty Ferry Castle and Monifieth. | https://broughtyferryactivetravel.com/ | DD5 2YS
|  |  | Greenspaces around Dundee |  | https://www.dundeecity.gov.uk/sites/default/files/publications/Dundee%20Green%20Network%2016.12.2016_A.pdf
|  |  | The MILL/ Urban Foresight | Mobility Innovation Living Lab, Dundee. The MILL is transforming Dundee ito a real-world test and experimentation environment for innovative mobility solutions. They provide expert support to large and small businesses. Including access to funding, infrastructure and end-users. | https://themill.scot/ | DD1 3EJ
|  |  | DEW Products | A Scottish company starting an eco-cleaning revolution fromDundee | https://www.dewproducts.co.uk | DD2 4UH
GOAL 12: RESPONSIBLE CONSUMPTION AND PRODUCITON | Ensure sustainable consumption and production patterns | Shop locally. Supporting local businesses keeps people employed and circulates money back in to the local community. Be conscious of packaging - the less the better Buy from companies with sustainable practices and don't harm the environment. Buy second hand whenever you can Make use of food sharing apps to reduce the amount of food waste you produce Choose reusable products - reusable water bottle, eco-bsgs for shopping. Join petitions and campaigns calling out businesses with unsustainable practices. | Dundee Community Wardrobe (Gate Church Carbon Saving Project) | The Dundee Community Wardrobe helps to stop good quality clothing going in the bin and teaches people how to live more sustainably. Encourages people to reuse, repair and share. *Potential to visit* | https://www.gatechurch.co.uk/communitywardrobe | DD1 4JA
|  |  | ScrapAntics | Scrapantics aims to celebrate and promote goings-on in Dundee in any way they can, whether it’s by providing resources, spreading word of mouth in the community or by holding small events. You can find a constantly evolving stock of materials ranging from wood and hand tools to paper, fabric, yarn, card and stationery. | https://scrapantics.co.uk/ | DD1 5BY
|  |  | Fairtrade Fortnight | 21 February to 6 March 2022 | https://www.fairtrade.org.uk/get-involved/current-campaigns/fairtrade-fortnight/ | DD4 6DG
GOAL 13: CLIMATE ACTION | Take urgent action to combat climate change and its impacts | Compost Choose reusable products Buy eco-friendly products Bike, walk or take public transport Consume less meat and animal products Reduce your use of paper | Dundee Community Fridge (Gate Church Carbon Saving Project) | *Details above* | https://www.gatechurch.co.uk/communityfridge | DD1 4JA
|  |  | Dundee Community Wardrobe (Gate Church Carbon Saving Project) | *Details above* | https://www.gatechurch.co.uk/communitywardrobe | DD1 4JA
|  |  | Dundee Cycle Hub | *Details above* |  | DD1 4EZ
(Plus lots more from above)
|  |  | Earth Hour Week | 21 - 26 March 2022 | https://www.earthhour.org/ | DD1 1QE
|  |  | World Environment Day | 2022-06-06 | https://www.worldenvironmentday.global/ | DD1 1QE
GOAL 14: LIFE BELOW WATER | Conserve and sustainably use the oceans, seas and marine resources for sustainable development | Never buy bottled water – boil, filter, chlorine, rainwater, do what you can. Reduce waste - lots of the waste we produce on land ends up in the sea. Stop using single use plastics wherever possible. Organise clean ups Buy local and certified fish - support small scale producers. | Conservation Areas | Link to map of Conservation Areas around Dundee |  | Baxter Park - DD4 6NL University Conservation Area - DD1 4HN Trottick - DD3 0EX Reres Hill - DD5 2SJ Maryfield - DD4 7AE
|  |  | Broughty Ferry Flood Protection Scheme |  | https://www.dundeecity.gov.uk/service-area/city-development/broughty-ferry-flood-protection-scheme
GOAL 15: LIFE ON LAND | Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss | Don't buy products tested on animals Don't shop for pets - adopt them from your local animal shelter. Recycle paper, glass, plastic, metal and old electronics. Compost Clean your local parks and forests | Camperdown Wildlife Centre | The aim of Camperdown Wildlife Centre's education programme is to supply the highest standard of zoological education to visitors using every possible resource that is available to education staff. | https://www.camperdownwildlifecentre.co.uk/conservation-research | DD2 4TF
|  |  | Dundee University Botanic Gardens | Visit and explore the wide range of plants, glasshouses, water garden and herb garden. | https://www.dundee.ac.uk/botanic/ | DD2 1QH
|  |  | The D'Arcy Thompson Zoology Museum | Visit? The University has a zoology museum that houses many fascinating specimens from around the world. | https://www.dundee.ac.uk/museum/collections/zoology/ | DD1 4HN
|  |  | RSPB Dundee |  | https://ww2.rspb.org.uk/groups/dundee | DD1 1QR
GOAL 16: PEACE AND JUSTICE, STRONG INSITUTIONS | Promote peaceful and inclusive societies for sustainable development, provide access to justice for all and build effective, accountable and inclusive institutions at all levels | Ask your local and national authorities to engage in initiatives that don't harm people or the planet. Know your rights. | One World Centre Dundee | *details above* | https://oneworldcentre.org.uk/ | DD1 1QE
GOAL 17: PARTNERSHIPS TO ACHIEVE GOAL | Strengthen the means of implementation and revitalize the global partnership for sustainable development | Share ideas Work with others

## events_table
id | name | description | postcode | goalID | website | contacts
1 | Dundee Bairns | Dundee Bairns is a charity working to benefit children in Dundee, addressing inequality in basic needs such as food and clothing. | DD4 0DX | 1 | https://dundeebairns.org/ | info@dundeebairns.org | insert into `events` (`id`, `name`, `description`, `postcode`, `goalID`, `website`, `contacts`) VALUES( | insert into `events` (`id`, `name`, `description`, `postcode`, `goalID`, `website`, `contacts`) VALUES(1,'Dundee Bairns','Dundee Bairns is a charity working to benefit children in Dundee, addressing inequality in basic needs such as food and clothing.','DD4 0DX',1,'https://dundeebairns.org/','info@dundeebairns.org'),
2 | Dundee Fighting for Fairness | The group is a voice for people in poverty in Dundee. | DD3 0AX | 1 | https://www.dundeefightingforfairness.co.uk/ | info@dundeefairness.org |  | (2,'Dundee Fighting for Fairness','The group is a voice for people in poverty in Dundee.','DD3 0AX',1,'https://www.dundeefightingforfairness.co.uk/','info@dundeefairness.org'),
3 | Positive Steps Partnership | The charity provides supported accommodation services for vulnerable adults | DD2 1DX | 1 | https://positivesteps.org.uk/ | info@positivesteps.org.uk |  | (3,'Positive Steps Partnership','The charity provides supported accommodation services for vulnerable adults','DD2 1DX',1,'https://positivesteps.org.uk/',' info@positivesteps.org.uk'),
4 | FareShare Dundee | Provides support to homeless and vulnerable individuals and offers training and volunteering opportunities. One of their projects - Transform Furniture - is a community based project that works towards overcoming poverty by providing quality reusable furniture and electrical household items to disadvantaged local groups, and training and employment opportunities for local people having difficulties in finding a job whilst reducing the amount of household goods that end up in landfill. | DD1 5AZ | 1 | https://www.transformcommunity.org.uk/ | admin@transformcd.org |  | (4,'FareShare Dundee','Provides support to homeless and vulnerable individuals and offers training and volunteering opportunities. One of their projects - Transform Furniture - is a community based project that works towards overcoming poverty by providing quality reusable furniture and electrical household items to disadvantaged local groups, and training and employment opportunities for local people having difficulties in finding a job whilst reducing the amount of household goods that end up in landfill.','DD1 5AZ',1,'https://www.transformcommunity.org.uk/','admin@transformcd.org'),
5 | Dundee Community Fridge (Gate Church Carbon Saving Project) | The Community Fridge at Gate Church is a communal place where surplus food is shared, by local businesses and individuals. The community fridge helps to cut food waste, build bonds within the community and re-distribute good quality food. Although the focus is on food waste, the Community Fridge also helps to reduce food poverty in Dundee. | DD1 4JA | 2 | https://www.gatechurch.co.uk/carbonsavingproject | info@gatechurch.co.uk |  | (5,'Dundee Community Fridge (Gate Church Carbon Saving Project)','The Community Fridge at Gate Church is a communal place where surplus food is shared, by local businesses and individuals. The community fridge helps to cut food waste, build bonds within the community and re-distribute good quality food. Although the focus is on food waste, the Community Fridge also helps to reduce food poverty in Dundee.','DD1 4JA',2,'https://www.gatechurch.co.uk/carbonsavingproject','info@gatechurch.co.uk'),
6 | Dundee and Angus Foodbank | The Dundee and Angus Foodbank provide emergency food parcels for those in need and support people in crisis. It is part of a nationwide network of foodbanks, supported by The Trussell Trust, working to combat poverty and hunger across the UK. Locations both in Dundee and Angus. | DD2 3QN | 2 | https://dundeeandangus.foodbank.org.uk/ | info@dundeeandangus.foodbank.org.uk |  | (6,'Dundee and Angus Foodbank','The Dundee and Angus Foodbank provide emergency food parcels for those in need and support people in crisis. It is part of a nationwide network of foodbanks, supported by The Trussell Trust, working to combat poverty and hunger across the UK. Locations both in Dundee and Angus.','DD2 3QN',2,'https://dundeeandangus.foodbank.org.uk/','info@dundeeandangus.foodbank.org.uk'),
7 | Taught by Muhammad | Taught By Muhammad is an outreach project aimed at building an understanding between Muslims and the wider community. The project also helps tackle social injustices within Dundee. They have several projects including curry kitchens where they cook for the homeless, a foodbank and schools outreach. *Potential for presentations in schools* | DD1 5HZ | 2 | www.taughtbymuhammad.com | info@taughtbymuhammad.com |  | (7,'Taught by Muhammad','Taught By Muhammad is an outreach project aimed at building an understanding between Muslims and the wider community. The project also helps tackle social injustices within Dundee. They have several projects including curry kitchens where they cook for the homeless, a foodbank and schools outreach. *Potential for presentations in schools*','DD1 5HZ',2,'www.taughtbymuhammad.com','info@taughtbymuhammad.com'),
8 | FareShare Dundee | FareShare Dundee collects/receives surplus quality food. The food is distributed to community organisations providing residential and day services for disadvantaged groups of people in Dundee, Perth & Kinross and Angus. | PH1 5PA | 2 | https://www.transformcommunity.org.uk/food-poverty | admin@transformcd.org |  | (8,'FareShare Dundee','FareShare Dundee collects/receives surplus quality food. The food is distributed to community organisations providing residential and day services for disadvantaged groups of people in Dundee, Perth & Kinross and Angus.','PH1 5PA',2,'https://www.transformcommunity.org.uk/food-poverty','admin@transformcd.org'),
9 | Embark Dundee | Ride On operates the e-bike sharing services in Dundee. The e-bikes provide a sustainable and affordable mobility solution for moving around the city. | DD1 4BX | 3 | https://rideondundee.com/ | support@rideondundee.com |  | (9,'Embark Dundee','Ride On operates the e-bike sharing services in Dundee. The e-bikes provide a sustainable and affordable mobility solution for moving around the city.','DD1 4BX',3,'https://rideondundee.com/','support@rideondundee.com'),
10 | Ancrum Outdoor Centre | The Ancrum Centre offers taster sessions, days out, skills development courses and coaching awards for people of all ages and abilities from the Dundee and wider Tayside region. Includes watersports, winter sports, cycling, climbing, hillwalking, first aid, team building and a group events. | DD2 2HZ | 3 | https://www.ancrum.com/ | ancrum.centre@leisureandculturedundee.com |  | (10,'Ancrum Outdoor Centre','The Ancrum Centre offers taster sessions, days out, skills development courses and coaching awards for people of all ages and abilities from the Dundee and wider Tayside region. Includes watersports, winter sports, cycling, climbing, hillwalking, first aid, team building and a group events.','DD2 2HZ',3,'https://www.ancrum.com/','ancrum.centre@leisureandculturedundee.com'),
11 | Aspire Programme Dundee | ASPIRE Dundee is a community engagement programme that uses performing arts across the curriculum to increase pupils’ health and wellbeing, self-confidence, self-esteem, learning and skills development. | DD1 1QE | 3 | https://education.gov.scot/improvement/practice-exemplars/aspire-programme-dundee/ | enquiries@educationscotland.gov.scot |  | (11,'Aspire Programme Dundee','ASPIRE Dundee is a community engagement programme that uses performing arts across the curriculum to increase pupils’ health and wellbeing, self-confidence, self-esteem, learning and skills development.','DD1 1QE',3,'https://education.gov.scot/improvement/practice-exemplars/aspire-programme-dundee/','enquiries@educationscotland.gov.scot'),
12 | Dundee Cycle Hub | The Dundee and Angus Cycle Hubs encourage people to lead healthier lives and reduce short car journeys and C02 emissions through cycling and recycling. They provide Bikeability training, bike hire, servicing and repairs and bike recycling. | DD1 4EZ | 3 | https://www.anguscyclehub.org/dundee-cycle-hub | info@anguscyclehub.org |  | (12,'Dundee Cycle Hub','The Dundee and Angus Cycle Hubs encourage people to lead healthier lives and reduce short car journeys and C02 emissions through cycling and recycling. They provide Bikeability training, bike hire, servicing and repairs and bike recycling.','DD1 4EZ',3,'https://www.anguscyclehub.org/dundee-cycle-hub','info@anguscyclehub.org'),
13 | Red Cross | Charity shop across Dundee (for donating) | DD1 1RG | 4 | https://www.redcross.org.uk/shop | contactus@redcross.org.uk |  | (13,'Red Cross','Charity shop across Dundee (for donating)','DD1 1RG',4,'https://www.redcross.org.uk/shop','contactus@redcross.org.uk'),
14 | Shelter | Charity shop across Dundee (for donating) | DD1 1PN | 4 | https://scotland.shelter.org.uk/shops/dundee_community_shop | info@shelterscotland.co.uk |  | (14,'Shelter','Charity shop across Dundee (for donating)','DD1 1PN',4,'https://scotland.shelter.org.uk/shops/dundee_community_shop','info@shelterscotland.co.uk'),
15 | Barnardo's | Charity shop across Dundee (for donating) | DD1 1SP | 4 | https://www.barnardos.org.uk/shops/our-shops/dundee | info@barnardos.co.uk |  | (15,'Barnardo's','Charity shop across Dundee (for donating)','DD1 1SP',4,'https://www.barnardos.org.uk/shops/our-shops/dundee','info@barnardos.co.uk'),
16 | British Heart Foundation | Charity shop across Dundee (for donating) | DD1 2DB | 4 | https://www.bhf.org.uk/ | heretohelp@bhf.org.uk |  | (16,'British Heart Foundation','Charity shop across Dundee (for donating)','DD1 2DB',4,'https://www.bhf.org.uk/','heretohelp@bhf.org.uk'),
17 | Central Library | Library | DD1 1DB | 4 | http://www.leisureandculturedundee.com/library/central-library-wellgate | central.library@leisureandculturedundee.com |  | (17,'Central Library','Library','DD1 1DB',4,'http://www.leisureandculturedundee.com/library/central-library-wellgate','central.library@leisureandculturedundee.com'),
18 | Soroptimists Dundee | The Soroptimists are a group of women working together to improve the lives of women and girls locally in Dundee, nationally and internationally. |  | 5 | https://www.facebook.com/soroptimistclubdundee/ | sally@sigbi.org |  | (18,'Soroptimists Dundee','The Soroptimists are a group of women working together to improve the lives of women and girls locally in Dundee, nationally and internationally.','',5,'https://www.facebook.com/soroptimistclubdundee/','sally@sigbi.org'),
19 | International Women's Day - 8th March | Event/campaign |  | 5 | https://www.internationalwomensday.com/ | info@internationalwomenday.co.uk |  | (19,'International Women's Day - 8th March','Event/campaign','',5,'https://www.internationalwomensday.com/','info@internationalwomenday.co.uk'),
20 | Scottish Water | St Leonard Park Regeneration - Scottish Water, NatureScot and SEPA are working with Dundee City Council to develop and improve the way storm water is managed and reduce flood risk in the St Mary's area of Dundee. Water mains investment - Dundee Laird Street. 1km of new water main was installed to improve the water network serving Dundee's Laird Street. | DD3 9HD | 6 | https://www.scottishwater.co.uk/in-your-area/investments-in-your-area/st-marys-drainage | info@scottishwater.co.uk |  | (20,'Scottish Water','St Leonard Park Regeneration - Scottish Water, NatureScot and SEPA are working with Dundee City Council to develop and improve the way storm water is managed and reduce flood risk in the St Mary's area of Dundee. Water mains investment - Dundee Laird Street. 1km of new water main was installed to improve the water network serving Dundee's Laird Street.','DD3 9HD',6,'https://www.scottishwater.co.uk/in-your-area/investments-in-your-area/st-marys-drainage','info@scottishwater.co.uk'),
21 | MSIP | Michelin Scotland Innovation Parc - a world class innovation parc in Dundee for sustainable mobility and decarbonisation. *Potential events and opportunities to visit in the future.* | DD4 8UQ | 7 | https://www.msipdundee.com/ | info@MSIP.co.uk |  | (21,'MSIP','Michelin Scotland Innovation Parc - a world class innovation parc in Dundee for sustainable mobility and decarbonisation. *Potential events and opportunities to visit in the future.*','DD4 8UQ',7,'https://www.msipdundee.com/','info@MSIP.co.uk'),
22 | MVV Environment Baldovie - Energy from Waste | Energy from waste facility - may be able to offer tours/ open days. Opportunity to learn about biomass/ energy from waste | DD4 0NS | 7 | https://www.mvv.de/en/about-us/group-of-companies/mvv-umwelt/subsidiaries/mvv-environment-ltd/baldovie-efw-chp-facility-dundee | contact@mvv.co.uk |  | (22,'MVV Environment Baldovie - Energy from Waste','Energy from waste facility - may be able to offer tours/ open days. Opportunity to learn about biomass/ energy from waste','DD4 0NS',7,'https://www.mvv.de/en/about-us/group-of-companies/mvv-umwelt/subsidiaries/mvv-environment-ltd/baldovie-efw-chp-facility-dundee','contact@mvv.co.uk'),
23 | Princes Street Charging Hub | EV charging hub with solar canopies. Potential to visit? | DD4 6AD | 7 | https://www.drivedundeeelectric.co.uk/princes-street | fleet@dundeecity.gov.uk |  | (23,'Princes Street Charging Hub','EV charging hub with solar canopies. Potential to visit?','DD4 6AD',7,'https://www.drivedundeeelectric.co.uk/princes-street','fleet@dundeecity.gov.uk'),
24 | Queen Street Charging Hub | EV charging hub with solar canopies. Potential to visit? | DD5 2HG | 7 | https://www.drivedundeeelectric.co.uk/queen-street | fleet@dundeecity.gov.uk |  | (24,'Queen Street Charging Hub','EV charging hub with solar canopies. Potential to visit?','DD5 2HG',7,'https://www.drivedundeeelectric.co.uk/queen-street','fleet@dundeecity.gov.uk'),
25 | Multi Storey car parks (MSPs) | Green Market, Olympia and Gellatly Street MSP's all have EV charging points. These sites encourage commuters to charge during the day and nearby residents to charge their EV at night. | DD1 1EX | 7 | https://www.drivedundeeelectric.co.uk/multi-storey-car-parks | fleet@dundeecity.gov.uk |  | (25,'Multi Storey car parks (MSPs)','Green Market, Olympia and Gellatly Street MSP's all have EV charging points. These sites encourage commuters to charge during the day and nearby residents to charge their EV at night.','DD1 1EX ',7,'https://www.drivedundeeelectric.co.uk/multi-storey-car-parks','fleet@dundeecity.gov.uk'),
26 | Multi Storey car parks (MSPs) | Green Market, Olympia and Gellatly Street MSP's all have EV charging points. These sites encourage commuters to charge during the day and nearby residents to charge their EV at night. | DD1 3DY | 7 | https://www.drivedundeeelectric.co.uk/multi-storey-car-parks | fleet@dundeecity.gov.uk |  | (26,'Multi Storey car parks (MSPs)','Green Market, Olympia and Gellatly Street MSP's all have EV charging points. These sites encourage commuters to charge during the day and nearby residents to charge their EV at night.','DD1 3DY',7,'https://www.drivedundeeelectric.co.uk/multi-storey-car-parks','fleet@dundeecity.gov.uk'),
27 | Dundee Science Centre | Events, activities, learning opportunities | DD1 4QB | 8 | https://www.dundeesciencecentre.org.uk/?gclid=Cj0KCQiAip-PBhDVARIsAPP2xc0DfaEICTubJ8ejpkqhdEUrRjuNVk7r55nA6MCzeyq6QCMv1sn3BygaAic7EALw_wcB | staff@dundeesciencecentre.org.uk |  | (27,'Dundee Science Centre','Events, activities, learning opportunities','DD1 4QB',8,'https://www.dundeesciencecentre.org.uk/?gclid=Cj0KCQiAip-PBhDVARIsAPP2xc0DfaEICTubJ8ejpkqhdEUrRjuNVk7r55nA6MCzeyq6QCMv1sn3BygaAic7EALw_wcB','staff@dundeesciencecentre.org.uk'),
28 | V&A Dundee | Scotland's first design museum. Significant economic impact bringing £21 million to the Dundee economy in the first 12 months of opening and the creation of jobs across Scotland. | DD1 4EZ | 8 | https://www.vam.ac.uk/info/plan-your-visit?gclid=Cj0KCQiAip-PBhDVARIsAPP2xc3B7pQ89FIbBCDg_D1rhdVo0TAsXx5JaqZz7rV1osUKhugv279otSwaAuRAEALw_wcB | hello@vam.ac.uk |  | (28,'V&A Dundee','Scotland's first design museum. Significant economic impact bringing £21 million to the Dundee economy in the first 12 months of opening and the creation of jobs across Scotland.','DD1 4EZ',8,'https://www.vam.ac.uk/info/plan-your-visit?gclid=Cj0KCQiAip-PBhDVARIsAPP2xc3B7pQ89FIbBCDg_D1rhdVo0TAsXx5JaqZz7rV1osUKhugv279otSwaAuRAEALw_wcB','hello@vam.ac.uk'),
29 | Elevator | Elevator works across Dundee, Angus and Perth, providing practical help, advice and support to business across all sectors, whatever stage they’re at. *potential to do a workshop with schools?* | DD1 5EN | 8 | https://www.elevatoruk.com/business-support/dundee/ | hello@elevator.ac.uk |  | (29,'Elevator','Elevator works across Dundee, Angus and Perth, providing practical help, advice and support to business across all sectors, whatever stage they’re at. *potential to do a workshop with schools?*','DD1 5EN',8,'https://www.elevatoruk.com/business-support/dundee/','hello@elevator.ac.uk'),
30 | Dundee Dairy Co | Local independent business in Dundee. Refill shop. | DD3 8AS | 8 | https://www.dundeedairyco.co.uk/ | contact@dundeedairyco.co.uk |  | (30,'Dundee Dairy Co','Local independent business in Dundee. Refill shop.','DD3 8AS',8,'https://www.dundeedairyco.co.uk/','contact@dundeedairyco.co.uk'),
31 | The Little Green Larder | Local independent business in Dundee. Refill shop. | DD2 1AE | 8 | https://thelittlegreenlarder.com/ | info@littlegreenlarder.co.uk |  | (31,'The Little Green Larder','Local independent business in Dundee. Refill shop.','DD2 1AE',8,'https://thelittlegreenlarder.com/','info@littlegreenlarder.co.uk'),
32 | Birchwood Food Emporium | Local independent business in Dundee. Refill shop. | DD1 3EQ | 8 | https://www.birchwoodemporium.com/ | info@birchwoodemporium.com |  | (32,'Birchwood Food Emporium','Local independent business in Dundee. Refill shop.','DD1 3EQ',8,'https://www.birchwoodemporium.com/','info@birchwoodemporium.com'),
33 | Love Your Planet | Local independent business in Dundee. Refill shop. | DD5 2AN | 8 | https://loveyourplanet.uk/ | Orders@love-your-planet.co.uk |  | (33,'Love Your Planet','Local independent business in Dundee. Refill shop.','DD5 2AN',8,'https://loveyourplanet.uk/','Orders@love-your-planet.co.uk'),
34 | MSIP | Michelin Scotland Innovation Parc - world class innovation parc in Dundee for sustainable mobility and decarbonisation. | DD4 8UQ | 9 | https://www.msipdundee.com/ | info@msipdundee.com |  | (34,'MSIP','Michelin Scotland Innovation Parc - world class innovation parc in Dundee for sustainable mobility and decarbonisation.','DD4 8UQ ',9,'https://www.msipdundee.com/','info@msipdundee.com'),
35 | MVV | Energy from waste facility in Dundee. *potential to visit at a later date* | DD4 0NS | 9 | https://www.mvv.de/en/about-us/group-of-companies/mvv-umwelt/subsidiaries/mvv-environment-ltd/baldovie-efw-chp-facility-dundee | contact@mvv.co.uk |  | (35,'MVV','Energy from waste facility in Dundee. *potential to visit at a later date*','DD4 0NS ',9,'https://www.mvv.de/en/about-us/group-of-companies/mvv-umwelt/subsidiaries/mvv-environment-ltd/baldovie-efw-chp-facility-dundee','contact@mvv.co.uk'),
36 | The MILL/ Urban Foresight | Mobility Innovation Living Lab, Dundee. The MILL is transforming Dundee ito a real-world test and experimentation environment for innovative mobility solutions. They provide expert support to large and small businesses. Including access to funding, infrastructure and end-users. *potential for school visits/workshops* | DD1 3EJ | 9 | https://themill.scot/ | hello@urbanforesight.org |  | (36,'The MILL/ Urban Foresight','Mobility Innovation Living Lab, Dundee. The MILL is transforming Dundee ito a real-world test and experimentation environment for innovative mobility solutions. They provide expert support to large and small businesses. Including access to funding, infrastructure and end-users. *potential for school visits/workshops*','DD1 3EJ ',9,'https://themill.scot/','hello@urbanforesight.org'),
37 | Danu Robotics | Robotics company with a robotic system for sorting recycling moving to MSIP. | DD4 8UQ | 9 | https://danurobotics.com/ | info@danurobotics.co.uk |  | (37,'Danu Robotics','Robotics company with a robotic system for sorting recycling moving to MSIP.','DD4 8UQ',9,'https://danurobotics.com/','info@danurobotics.co.uk'),
38 | S5GConnect Dundee | S5GConnect Dundee is opening a range of support, facilities and opportunities for businesses of all sizes to test and develop new 5G applications and services. *Find out more* | DD1 1QE | 9 | https://scotland5gcentre.org/s5gconnect/s5gconnect-dundee/ | info@scotland5gcentre.org |  | (38,'S5GConnect Dundee','S5GConnect Dundee is opening a range of support, facilities and opportunities for businesses of all sizes to test and develop new 5G applications and services. *Find out more*','DD1 1QE',9,'https://scotland5gcentre.org/s5gconnect/s5gconnect-dundee/ ','info@scotland5gcentre.org'),
39 | Dundee Esports Arena | Upcoming project | DD1 3RT | 9 |  | events.activities@dundeecity.gov.uk |  | (39,'Dundee Esports Arena','Upcoming project','DD1 3RT',9,'','events.activities@dundeecity.gov.uk'),
40 | Dundee Eden Project | Upcoming project | DD1 3RT | 9 |  | events.activities@dundeecity.gov.uk |  | (40,'Dundee Eden Project','Upcoming project','DD1 3RT',9,'','events.activities@dundeecity.gov.uk'),
41 | Dundee Science Centre | Events, activities, learning opportunities | DD1 4QB | 9 | https://www.dundeesciencecentre.org.uk/?gclid=Cj0KCQiAip-PBhDVARIsAPP2xc0DfaEICTubJ8ejpkqhdEUrRjuNVk7r55nA6MCzeyq6QCMv1sn3BygaAic7EALw_wcB | staff@dundeesciencecentre.org.uk |  | (41,'Dundee Science Centre','Events, activities, learning opportunities','DD1 4QB',9,'https://www.dundeesciencecentre.org.uk/?gclid=Cj0KCQiAip-PBhDVARIsAPP2xc0DfaEICTubJ8ejpkqhdEUrRjuNVk7r55nA6MCzeyq6QCMv1sn3BygaAic7EALw_wcB','staff@dundeesciencecentre.org.uk'),
42 | Dundee's Waterfront | Regeneration of Dundee City Waterfront. 30 year long project. (Visit and learn about the history, how the transformational changes have postivley impacted the city.) | DD1 3AZ | 9 | https://www.dundeewaterfront.com/ | info@waterfront.co.uk |  | (42,'Dundee's Waterfront','Regeneration of Dundee City Waterfront. 30 year long project. (Visit and learn about the history, how the transformational changes have postivley impacted the city.)','DD1 3AZ',9,'https://www.dundeewaterfront.com/','info@waterfront.co.uk'),
43 | V&A Dundee | Scotland's first design museum. Significant economic impact bringing £21 million to the Dundee economy in the first 12 months of opening and the creation of jobs across Scotland. | DD1 4EZ | 9 | https://www.vam.ac.uk/info/plan-your-visit?gclid=Cj0KCQiAip-PBhDVARIsAPP2xc3B7pQ89FIbBCDg_D1rhdVo0TAsXx5JaqZz7rV1osUKhugv279otSwaAuRAEALw_wcB | hello@vam.ac.uk |  | (43,'V&A Dundee','Scotland's first design museum. Significant economic impact bringing £21 million to the Dundee economy in the first 12 months of opening and the creation of jobs across Scotland.','DD1 4EZ',9,'https://www.vam.ac.uk/info/plan-your-visit?gclid=Cj0KCQiAip-PBhDVARIsAPP2xc3B7pQ89FIbBCDg_D1rhdVo0TAsXx5JaqZz7rV1osUKhugv279otSwaAuRAEALw_wcB','hello@vam.ac.uk'),
44 | University of Dundee | One of the UK's leading universities, internationally recognised for its expertise across a range of disciplines . | DD1 4HN | 9 | https://www.dundee.ac.uk/ | hr@dundee.ac.uk |  | (44,'University of Dundee','One of the UK's leading universities, internationally recognised for its expertise across a range of disciplines .','DD1 4HN',9,'https://www.dundee.ac.uk/','hr@dundee.ac.uk'),
45 | One World Centre Dundee | One World Centre promotes global justice and equality through education by supporting teachers, schools and community groups in Angus, Dundee, Fife and Perth & Kinross to engage in Global Citizenship through Professional Learning. | DD1 1QE | 10 | https://oneworldcentre.org.uk/ | info@oneworldcentre.co.uk |  | (45,'One World Centre Dundee','One World Centre promotes global justice and equality through education by supporting teachers, schools and community groups in Angus, Dundee, Fife and Perth & Kinross to engage in Global Citizenship through Professional Learning.','DD1 1QE',10,'https://oneworldcentre.org.uk/','info@oneworldcentre.co.uk'),
46 | Embark Dundee | Ride On operates the e-bike sharing services in Dundee. The e-bikes provide a sustainable and affordable mobility solution for moving around the city. | DD1 4BX | 11 | https://rideondundee.com/ | support@rideondundee.com |  | (46,'Embark Dundee','Ride On operates the e-bike sharing services in Dundee. The e-bikes provide a sustainable and affordable mobility solution for moving around the city.','DD1 4BX',11,'https://rideondundee.com/','support@rideondundee.com'),
47 | Dundee Cycle Hub | The Dundee and Angus Cycle Hubs encourage people to lead healthier lives and reduce short car journeys and C02 emissions through cycling and recycling. They provide Bikeability training, bike hire, servicing and repairs and bike recycling. | DD1 4EZ | 11 | https://www.anguscyclehub.org/dundee-cycle-hub | info@dundeecyclehub.org |  | (47,'Dundee Cycle Hub','The Dundee and Angus Cycle Hubs encourage people to lead healthier lives and reduce short car journeys and C02 emissions through cycling and recycling. They provide Bikeability training, bike hire, servicing and repairs and bike recycling.','DD1 4EZ',11,'https://www.anguscyclehub.org/dundee-cycle-hub','info@dundeecyclehub.org'),
48 | Aitken's | Local independent business in Dundee | DD1 4JG | 11 | https://aitkenwines.com/ | team@aitkenwines.com |  | (48,'Aitken's','Local independent business in Dundee','DD1 4JG',11,'https://aitkenwines.com/','team@aitkenwines.com'),
49 | Time Lifestyle Boutique | Local independent business in Dundee | DD1 1SL | 11 | https://www.tripadvisor.co.uk/Attraction_Review-g186518-d8004442-Reviews-Time_Lifestyle_Boutique-Dundee_Scotland.html | info@timelifestyle.co.uk |  | (49,'Time Lifestyle Boutique','Local independent business in Dundee','DD1 1SL',11,'https://www.tripadvisor.co.uk/Attraction_Review-g186518-d8004442-Reviews-Time_Lifestyle_Boutique-Dundee_Scotland.html','info@timelifestyle.co.uk'),
50 | Dundee Delights | Local independent business in Dundee | DD5 3EJ | 11 | https://www.facebook.com/Madinadelights/ | info@dundeedelights.co.uk |  | (50,'Dundee Delights','Local independent business in Dundee','DD5 3EJ',11,'https://www.facebook.com/Madinadelights/','info@dundeedelights.co.uk'),
51 | Faerie Tree | Local independent business in Dundee | DD2 2JA | 11 | https://thefaerietree.co.uk/ | info@faerietree.co.uk |  | (51,'Faerie Tree','Local independent business in Dundee','DD2 2JA',11,'https://thefaerietree.co.uk/','info@faerietree.co.uk'),
52 | Gidi Grill | Local independent business in Dundee | DD1 3JA | 11 | https://www.gidigrill.com/ | info@gidigrill.co.uk |  | (52,'Gidi Grill','Local independent business in Dundee','DD1 3JA',11,'https://www.gidigrill.com/','info@gidigrill.co.uk'),
53 | The Selkie | Local independent business in Dundee | DD1 3DJ | 11 | https://www.theselkie.scot/ | Hello@theselkie.scot |  | (53,'The Selkie','Local independent business in Dundee','DD1 3DJ',11,'https://www.theselkie.scot/','Hello@theselkie.scot'),
54 | The Butcher the Baker | Local independent business in Dundee | DD1 5JH | 11 | http://thebutcherthebakerscotland.com/ | info@butcherdundee.ac.uk |  | (54,'The Butcher the Baker','Local independent business in Dundee','DD1 5JH',11,'http://thebutcherthebakerscotland.com/','info@butcherdundee.ac.uk'),
55 | Electric Buses | Xplore Dundee, Stage Coach Buses, Ember. *Potential to visit? See charging?* | DD1 2AP | 11 | https://www.xploredundee.com/MissionZero https://www.stagecoachbus.com/promos-and-offers/east-scotland/route-20-and-21 | travelcare@mcgillsbuses.co.uk |  | (55,'Electric Buses','Xplore Dundee, Stage Coach Buses, Ember. *Potential to visit? See charging?*','DD1 2AP',11,'https://www.xploredundee.com/MissionZero https://www.stagecoachbus.com/promos-and-offers/east-scotland/route-20-and-21','travelcare@mcgillsbuses.co.uk'),
56 | Broughty Ferry and Monifieth Active Travel Improvements | Dundee City Council and Angus Council are working together to improve the National Cycle Network Route 1 between Broughty Ferry Castle and Monifieth. | DD5 2YS | 11 | https://broughtyferryactivetravel.com/ | info@broughtyferryactivetravel.com |  | (56,'Broughty Ferry and Monifieth Active Travel Improvements','Dundee City Council and Angus Council are working together to improve the National Cycle Network Route 1 between Broughty Ferry Castle and Monifieth.','DD5 2YS',11,'https://broughtyferryactivetravel.com/','info@broughtyferryactivetravel.com'),
57 | The MILL/ Urban Foresight | Mobility Innovation Living Lab, Dundee. The MILL is transforming Dundee ito a real-world test and experimentation environment for innovative mobility solutions. They provide expert support to large and small businesses. Including access to funding, infrastructure and end-users. | DD1 3EJ | 11 | https://themill.scot/ | hello@urbanforesight.org |  | (57,'The MILL/ Urban Foresight','Mobility Innovation Living Lab, Dundee. The MILL is transforming Dundee ito a real-world test and experimentation environment for innovative mobility solutions. They provide expert support to large and small businesses. Including access to funding, infrastructure and end-users.','DD1 3EJ',11,'https://themill.scot/','hello@urbanforesight.org'),
58 | DEW Products | A Scottish company starting an eco-cleaning revolution fromDundee | DD2 4UH | 11 | https://www.dewproducts.co.uk | info@dewproducts.ac.uk |  | (58,'DEW Products','A Scottish company starting an eco-cleaning revolution fromDundee','DD2 4UH',11,'https://www.dewproducts.co.uk','info@dewproducts.ac.uk'),
59 | Dundee Community Wardrobe (Gate Church Carbon Saving Project) | The Dundee Community Wardrobe helps to stop good quality clothing going in the bin and teaches people how to live more sustainably. Encourages people to reuse, repair and share. *Potential to visit* | DD1 4JA | 12 | https://www.gatechurch.co.uk/communitywardrobe | info@gatechurch.co.uk |  | (59,'Dundee Community Wardrobe (Gate Church Carbon Saving Project)','The Dundee Community Wardrobe helps to stop good quality clothing going in the bin and teaches people how to live more sustainably. Encourages people to reuse, repair and share. *Potential to visit*','DD1 4JA',12,'https://www.gatechurch.co.uk/communitywardrobe','info@gatechurch.co.uk'),
60 | ScrapAntics | Scrapantics aims to celebrate and promote goings-on in Dundee in any way they can, whether it’s by providing resources, spreading word of mouth in the community or by holding small events. You can find a constantly evolving stock of materials ranging from wood and hand tools to paper, fabric, yarn, card and stationery. | DD1 5BY | 12 | https://scrapantics.co.uk/ | INFO@SCRAPANTICS.CO.UK |  | (60,'ScrapAntics','Scrapantics aims to celebrate and promote goings-on in Dundee in any way they can, whether it’s by providing resources, spreading word of mouth in the community or by holding small events. You can find a constantly evolving stock of materials ranging from wood and hand tools to paper, fabric, yarn, card and stationery.','DD1 5BY',12,'https://scrapantics.co.uk/','INFO@SCRAPANTICS.CO.UK'),
61 | Fairtrade Fortnight | 21 February to 6 March 2022 | DD4 6DG | 12 | https://www.fairtrade.org.uk/get-involved/current-campaigns/fairtrade-fortnight/ | info@fairtrade.org.uk |  | (61,'Fairtrade Fortnight','21 February to 6 March 2022','DD4 6DG',12,'https://www.fairtrade.org.uk/get-involved/current-campaigns/fairtrade-fortnight/','info@fairtrade.org.uk'),
62 | Dundee Community Fridge (Gate Church Carbon Saving Project) | Gate Church Carbon Saving Project | DD1 4JA | 13 | https://www.gatechurch.co.uk/communityfridge | info@gatechurch.co.uk |  | (62,'Dundee Community Fridge (Gate Church Carbon Saving Project)','Gate Church Carbon Saving Project','DD1 4JA',13,'https://www.gatechurch.co.uk/communityfridge','info@gatechurch.co.uk'),
63 | Dundee Community Wardrobe | Gate Church Carbon Saving Project | DD1 4JA | 13 | https://www.gatechurch.co.uk/communitywardrobe | info@gatechurch.co.uk |  | (63,'Dundee Community Wardrobe ','Gate Church Carbon Saving Project','DD1 4JA',13,'https://www.gatechurch.co.uk/communitywardrobe','info@gatechurch.co.uk'),
64 | Dundee Cycle Hub | Recycled, Refurbished & New Bikes, Components & Accessories | DD1 4EZ | 13 | https://www.anguscyclehub.org/dundee-cycle-hub | info@dundeecyclehub.org |  | (64,'Dundee Cycle Hub','Recycled, Refurbished & New Bikes, Components & Accessories','DD1 4EZ',13,'https://www.anguscyclehub.org/dundee-cycle-hub','info@dundeecyclehub.org'),
66 | Earth Hour Week | 21 - 26 March 2022 | DD1 1QE | 13 | https://www.earthhour.org/ | museum@dundee.ac.uk |  | (66,'Earth Hour Week','21 - 26 March 2022','DD1 1QE',13,'https://www.earthhour.org/','museum@dundee.ac.uk'),
67 | World Environment Day | 2022-06-06 | DD1 1QE | 13 | https://www.worldenvironmentday.global/ | info@worldenvironmentday.co.uk |  | (67,'World Environment Day','44718','DD1 1QE',13,'https://www.worldenvironmentday.global/','info@worldenvironmentday.co.uk'),
68 | Baxter Park | Conservation Area | DD4 6NL | 14 | https://www.dundeecity.gov.uk/service-area/neighbourhood-services/environment/baxter-park-and-pavilion | events.activities@dundeecity.gov.uk |  | (68,'Baxter Park','Conservation Area','DD4 6NL',14,'https://www.dundeecity.gov.uk/service-area/neighbourhood-services/environment/baxter-park-and-pavilion','events.activities@dundeecity.gov.uk'),
69 | University Conservation Area | Conservation Area | DD1 4HN | 14 | https://www.dundeecity.gov.uk/service-area/city-development/planning-and-economic-development/development-management/university-conservation-area | events.activities@dundeecity.gov.uk |  | (69,'University Conservation Area','Conservation Area','DD1 4HN',14,'https://www.dundeecity.gov.uk/service-area/city-development/planning-and-economic-development/development-management/university-conservation-area','events.activities@dundeecity.gov.uk'),
70 | Trottick | Conservation Area | DD3 0EX | 14 | https://www.dundeecity.gov.uk/service-area/city-development/development-management/trottick-conservation-area | events.activities@dundeecity.gov.uk |  | (70,'Trottick','Conservation Area','DD3 0EX',14,'https://www.dundeecity.gov.uk/service-area/city-development/development-management/trottick-conservation-area','events.activities@dundeecity.gov.uk'),
71 | Reres Hill | Conservation Area | DD5 2SJ | 14 | https://www.dundeecity.gov.uk/service-area/city-development/development-management/reres-hill-conservation-area | events.activities@dundeecity.gov.uk |  | (71,'Reres Hill','Conservation Area','DD5 2SJ',14,'https://www.dundeecity.gov.uk/service-area/city-development/development-management/reres-hill-conservation-area','events.activities@dundeecity.gov.uk'),
72 | Maryfield | Conservation Area | DD4 7AE | 14 | https://www.dundeecity.gov.uk/service-area/city-development/planning-and-economic-development/development-management/maryfield-conservation-area | events.activities@dundeecity.gov.uk |  | (72,'Maryfield','Conservation Area','DD4 7AE',14,'https://www.dundeecity.gov.uk/service-area/city-development/planning-and-economic-development/development-management/maryfield-conservation-area','events.activities@dundeecity.gov.uk'),
73 | Camperdown Wildlife Centre | The aim of Camperdown Wildlife Centre's education programme is to supply the highest standard of zoological education to visitors using every possible resource that is available to education staff. | DD2 4TF | 15 | https://www.camperdownwildlifecentre.co.uk/conservation-research | info@camperdownwildlifecentre.com |  | (73,'Camperdown Wildlife Centre','The aim of Camperdown Wildlife Centre's education programme is to supply the highest standard of zoological education to visitors using every possible resource that is available to education staff.','DD2 4TF',15,'https://www.camperdownwildlifecentre.co.uk/conservation-research','info@camperdownwildlifecentre.com'),
74 | Dundee University Botanic Gardens | Visit and explore the wide range of plants, glasshouses, water garden and herb garden. | DD2 1QH | 15 | https://www.dundee.ac.uk/botanic/ | museum@dundee.ac.uk |  | (74,'Dundee University Botanic Gardens','Visit and explore the wide range of plants, glasshouses, water garden and herb garden.','DD2 1QH',15,'https://www.dundee.ac.uk/botanic/','museum@dundee.ac.uk'),
75 | The D'Arcy Thompson Zoology Museum | Visit? The University has a zoology museum that houses many fascinating specimens from around the world. | DD1 4HN | 15 | https://www.dundee.ac.uk/museum/collections/zoology/ | museum@dundee.ac.uk |  | (75,'The D'Arcy Thompson Zoology Museum','Visit? The University has a zoology museum that houses many fascinating specimens from around the world.','DD1 4HN',15,'https://www.dundee.ac.uk/museum/collections/zoology/','museum@dundee.ac.uk'),
76 | RSPB Dundee | Dundee Local Group | DD1 1QR | 15 | https://ww2.rspb.org.uk/groups/dundee | info@rspb.co.uk |  | (76,'RSPB Dundee','Dundee Local Group','DD1 1QR',15,'https://ww2.rspb.org.uk/groups/dundee','info@rspb.co.uk'),
77 | One World Centre Dundee | One World Centre promotes global justice and equality through education by supporting teachers, schools and community groups in Angus, Dundee, Fife and Perth & Kinross to engage in Global Citizenship through Professional Learning. | DD1 1QE | 16 | https://oneworldcentre.org.uk/ | info@oneworldcentre.co.uk |  | (77,'One World Centre Dundee','One World Centre promotes global justice and equality through education by supporting teachers, schools and community groups in Angus, Dundee, Fife and Perth & Kinross to engage in Global Citizenship through Professional Learning.','DD1 1QE',16,'https://oneworldcentre.org.uk/','info@oneworldcentre.co.uk'),

## coordinates
postcode | lat | long
DD1 1DB | 56.4647 | -2.9693 | insert into `coord`(`postcode`, `lat`, `long`) values( | insert into `coord`(`postcode`, `lat`, `long`) values('DD1 1DB',56.4647174282653,-2.96930793466534 | insert into `coord`(`postcode`, `lat`, `long`) values('DD1 1DB',56.4647174282653,-2.96930793466534);
DD1 1EX | 56.4624 | -2.9758 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 1EX',56.4624321186019,-2.97580222142871 | ('DD1 1EX',56.4624321186019,-2.97580222142871),
DD1 1PN | 56.461 | -2.9747 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 1PN',56.4609700297359,-2.97471769630174 | ('DD1 1PN',56.4609700297359,-2.97471769630174),
DD1 1QE | 56.4602 | -2.9756 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 1QE',56.460197719339,-2.9755639465559 | ('DD1 1QE',56.460197719339,-2.9755639465559),
DD1 1QR | 56.4588 | -2.9755 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 1QR',56.4587747149862,-2.97551280582927 | ('DD1 1QR',56.4587747149862,-2.97551280582927),
DD1 1RG | 56.4608 | -2.9708 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 1RG',56.4608004085128,-2.9708298272469 | ('DD1 1RG',56.4608004085128,-2.9708298272469),
DD1 1SL | 56.4617 | -2.9713 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 1SL',56.4616962280805,-2.97125797910151 | ('DD1 1SL',56.4616962280805,-2.97125797910151),
DD1 1SP | 56.4619 | -2.9714 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 1SP',56.4619002567239,-2.97139839444701 | ('DD1 1SP',56.4619002567239,-2.97139839444701),
DD1 2AP | 56.4618 | -2.9698 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 2AP',56.4618473067728,-2.96975236746531 | ('DD1 2AP',56.4618473067728,-2.96975236746531),
DD1 2DB | 56.4639 | -2.9694 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 2DB',56.4639343262982,-2.96944658862882 | ('DD1 2DB',56.4639343262982,-2.96944658862882),
DD1 3AZ | 56.4588 | -2.9672 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 3AZ',56.4587696277131,-2.96717860860556 | ('DD1 3AZ',56.4587696277131,-2.96717860860556),
DD1 3DJ | 56.4605 | -2.967 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 3DJ',56.4604961307514,-2.96702023095622 | ('DD1 3DJ',56.4604961307514,-2.96702023095622),
DD1 3DY | 56.4619 | -2.9665 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 3DY',56.4618958223086,-2.9664716558291 | ('DD1 3DY',56.4618958223086,-2.9664716558291),
DD1 3EJ | 56.4611 | -2.9672 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 3EJ',56.4611150916059,-2.96724889444707 | ('DD1 3EJ',56.4611150916059,-2.96724889444707),
DD1 3EQ | 56.4611 | -2.9674 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 3EQ',56.4611265361734,-2.96736564444707 | ('DD1 3EQ',56.4611265361734,-2.96736564444707),
DD1 3JA | 56.4623 | -2.9603 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 3JA',56.462304533595,-2.96033073862892 | ('DD1 3JA',56.462304533595,-2.96033073862892),
DD1 3RT | 56.4594 | -2.9675 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 3RT',56.4594109704993,-2.9675322251382 | ('DD1 3RT',56.4594109704993,-2.9675322251382),
DD1 4BE | 56.459 | -2.9706 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 4BE',56.4590121672971,-2.97059373677441 | ('DD1 4BE',56.4590121672971,-2.97059373677441),
DD1 4BX | 56.4572 | -2.9697 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 4BX',56.4572064736212,-2.96973358837506 | ('DD1 4BX',56.4572064736212,-2.96973358837506),
DD1 4EZ | 56.4574 | -2.9671 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 4EZ',56.4573867299765,-2.96712230742987 | ('DD1 4EZ',56.4573867299765,-2.96712230742987),
DD1 4HN | 56.4574 | -2.9783 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 4HN',56.4573841468167,-2.97827765212 | ('DD1 4HN',56.4573841468167,-2.97827765212),
DD1 4JA | 56.4561 | -2.9893 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 4JA',56.4561197022592,-2.98925124815664 | ('DD1 4JA',56.4561197022592,-2.98925124815664),
DD1 4JG | 56.4568 | -2.9889 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 4JG',56.4568139827921,-2.98889643281106 | ('DD1 4JG',56.4568139827921,-2.98889643281106),
DD1 4QB | 56.456 | -2.9771 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 4QB',56.4559572357452,-2.97707900835473 | ('DD1 4QB',56.4559572357452,-2.97707900835473),
DD1 5AZ | 56.4628 | -2.9867 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 5AZ',56.4627833948002,-2.98672111164716 | ('DD1 5AZ',56.4627833948002,-2.98672111164716),
DD1 5BY | 56.462 | -2.9848 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 5BY',56.4620294599057,-2.98483622142877 | ('DD1 5BY',56.4620294599057,-2.98483622142877),
DD1 5EN | 56.4596 | -2.9835 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 5EN',56.4596463134617,-2.98349656771955 | ('DD1 5EN',56.4596463134617,-2.98349656771955),
DD1 5HZ | 56.4592 | -2.9888 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 5HZ',56.4591947851073,-2.98884414048374 | ('DD1 5HZ',56.4591947851073,-2.98884414048374),
DD1 5JH | 56.4595 | -2.9924 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD1 5JH',56.459517322158,-2.99242140768389 | ('DD1 5JH',56.459517322158,-2.99242140768389),
DD2 1AE | 56.4559 | -2.9922 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD2 1AE',56.4559089231083,-2.99223250212007 | ('DD2 1AE',56.4559089231083,-2.99223250212007),
DD2 1DX | 56.4651 | -3.0599 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD2 1DX',56.4650697084108,-3.05989913955187 | ('DD2 1DX',56.4650697084108,-3.05989913955187),
DD2 1QH | 56.4564 | -3.0251 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD2 1QH',56.4563931567069,-3.02507528188135 | ('DD2 1QH',56.4563931567069,-3.02507528188135),
DD2 2HZ | 56.4686 | -3.0067 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD2 2HZ',56.4686469461614,-3.00665535211944 | ('DD2 2HZ',56.4686469461614,-3.00665535211944),
DD2 2JA | 56.4674 | -3.0078 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD2 2JA',56.4673729502997,-3.00782947842376 | ('DD2 2JA',56.4673729502997,-3.00782947842376),
DD2 3QN | 56.4797 | -3.0135 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD2 3QN',56.4796955789572,-3.01345969419195 | ('DD2 3QN',56.4796955789572,-3.01345969419195),
DD2 4DD | 56.4679 | -3.0381 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD2 4DD',56.4678770579228,-3.0380919137557 | ('DD2 4DD',56.4678770579228,-3.0380919137557),
DD2 4TF | 56.4849 | -3.043 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD2 4TF',56.4848518333986,-3.04298499054603 | ('DD2 4TF',56.4848518333986,-3.04298499054603),
DD2 4UH | 56.4764 | -3.0551 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD2 4UH',56.4763664665362,-3.05510475153075 | ('DD2 4UH',56.4763664665362,-3.05510475153075),
DD3 0AX | 56.4875 | -2.9867 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD3 0AX',56.4874668948235,-2.98669981535522 | ('DD3 0AX',56.4874668948235,-2.98669981535522),
DD3 0EX | 56.4904 | -2.9739 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD3 0EX',56.4904037063258,-2.9739435193185 | ('DD3 0EX',56.4904037063258,-2.9739435193185),
DD3 8AS | 56.4768 | -2.9772 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD3 8AS',56.4768478272627,-2.97721425026435 | ('DD3 8AS',56.4768478272627,-2.97721425026435),
DD3 9HD | 56.4928 | -3.0001 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD3 9HD',56.4927932343217,-3.00014679259082 | ('DD3 9HD',56.4927932343217,-3.00014679259082),
DD4 0DX | 56.4881 | -2.9269 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD4 0DX',56.4880790769386,-2.92690288120894 | ('DD4 0DX',56.4880790769386,-2.92690288120894),
DD4 0NS | 56.4849 | -2.9019 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD4 0NS',56.4848820015714,-2.90185486282022 | ('DD4 0NS',56.4848820015714,-2.90185486282022),
DD4 6AD | 56.4657 | -2.9624 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD4 6AD',56.4656530838063,-2.96242149444683 | ('DD4 6AD',56.4656530838063,-2.96242149444683),
DD4 6DG | 56.4671 | -2.9582 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD4 6DG',56.4671379771296,-2.95817920397418 | ('DD4 6DG',56.4671379771296,-2.95817920397418),
DD4 6NL | 56.4734 | -2.9541 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD4 6NL',56.4733992150534,-2.95413708651953 | ('DD4 6NL',56.4733992150534,-2.95413708651953),
DD4 7AE | 56.4751 | -2.9565 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD4 7AE',56.4751417786737,-2.95648757328272 | ('DD4 7AE',56.4751417786737,-2.95648757328272),
DD4 8UQ | 56.482 | -2.8919 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD4 8UQ',56.4820309095341,-2.89191907100173 | ('DD4 8UQ',56.4820309095341,-2.89191907100173),
DD5 2AN | 56.4666 | -2.8717 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD5 2AN',56.4666363937236,-2.8717321211744 | ('DD5 2AN',56.4666363937236,-2.8717321211744),
DD5 2HG | 56.4681 | -2.8754 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD5 2HG',56.4681229833921,-2.87535746164689 | ('DD5 2HG',56.4681229833921,-2.87535746164689),
DD5 2SJ | 56.47 | -2.8541 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD5 2SJ',56.4699656298224,-2.854067650773 | ('DD5 2SJ',56.4699656298224,-2.854067650773),
DD5 2YS | 56.4756 | -2.8964 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD5 2YS',56.475648398019,-2.89641127807174 | ('DD5 2YS',56.475648398019,-2.89641127807174),
DD5 3EJ | 56.4727 | -2.868 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('DD5 3EJ',56.4726982233066,-2.86795667513751 | ('DD5 3EJ',56.4726982233066,-2.86795667513751),
PH1 5PA | 56.3965 | -3.4335 | insert into `coord`(`postcode`, `lat`, `long`) values( | ('PH1 5PA',56.3965254673837,-3.43351895237728 | ('PH1 5PA',56.3965254673837,-3.43351895237728);