## Sheet1
AGILE PRODUCT BACKLOG
ID | As a(n)... | I want to be be able to... | So that... | Priority | Sprint | Status | Story Points | Date Added | Date Completed
1 | Member of the public | select 1 of the 17 goals | I can find out more information about it | Must | 1 | Done | 5 | 24/01/2022 | 24/01/2022
2 | Member of the public | see a list of items aligned with each goal | I can learn more about it | Must | 1 | Done | 3 | 24/01/2022 | 25/01/2022
3 | Admin | make edits to existing items and add new items | content can be updated if necessary | Must | 1 | Done | 8 | 24/01/2022 | 26/01/2022
4 | Admin | add users | they can add/remove/edit items | Must | 1 | Done | 8 | 24/01/2022 | 26/01/2022
4.1 | Admin User | add a new item(event/organisation) | more content can be added to the website | Must | 1 | Done | 4 | 25/01/2022 | 26/01/2022
4.2 | Admin user | delete an item | any unnecessary content can be removed | Must | 1 | Done | 3 | 25/01/2022 | 25/01/2022
4.3 | Admin user | edit an item | content can be updated if necessary | Must | 1 | Done | 8 | 25/01/2022 | 27/01/2022
5 | Member of the public | view items associated with a goal on a map | I can find them easily | Must | 1 | Done | 8 | 24/01/2022 | 27/01/2022
6 | Member of the public | have each item show more information about events including contacts | I can be more informed | Must | 1 | Done | 3 | 24/01/2022 | 25/01/2022
7 | Member of the public | create a list of favourited items | I can easily access items that interest me | Should | 1 | Done | 8 | 24/01/2022 | 28/01/2022
8 | Member of the public | view sustainable activities near my location | I can see what's on and get involved | Could | 1 | Done | 8 | 24/01/2022 | 27/01/2022
9 | User | register to the site | use the site functionality | Must | 2 | Done | 8 | 31/01/2022 | 31/01/2022
10 | Colour - blind person | view events as sustainable Dundee petals | I can differentiate between my and the event location markers easily | Must | 2 | Done | 3 | 28/01/2022 | 31/01/2022
11 | Older person | view larger icons on the map | I can immediately see what each item is | Must | 2 | Done | 2 | 28/01/2022 | 31/01/2022
12 | Member of the public | view the addresses of items selected on map | I can see where they are located exactly | Must | 2 | Done | 5 | 28/01/2022 | 2022-01-02
13 | Teen | use the app on my mobile device | it's accessible on the go | Must | 2 | Done | 1 | 24/01/2022 | 31/01/2022
14 | Member of the public | change my password | my account is more secure | Must | 2 | Done | 3 | 24/01/2023 | 31/01/2023
15 | Member of the public | see local news about sustainability | I can be informed | Must | 2 | Done | 3 | 26/01/2022 | 2022-04-02
16 | Teen | add friends who are also registered | we can compare our activity experiences | Must | 2 | Done | 8 | 31/01/2022 | 2022-02-02
17 | Teen | accept friend requests | I can be friends with the sender | Must | 2 | Done | 8 | 31/01/2022 | 02/022022
18 | Teen | check into a location which will upload to a leaderboard amongst friends | I can compare my amount of check-ins with my friends' | Must | 2 | Done | 16 | 26/01/2022 | 2022-01-02
18.1 | User | check into an event through the website | I can see what places I have visited | Must | 2 | Done | 8 | 26/01/2022 | 2022-01-02
18.2 | Teen | upload to a leaderboard amongst friends | friends can see my amount of check-ins | Must | 2 | Done | 8 | 26/01/2022 | 2022-01-02
19 | Teen | check into a location through social media | I can share my experiences | Must | 2 | Done | 5 | 24/01/2022 | 2022-01-02
20 | Member of the public | see data from the UN (i.e. recycling points in Dundee) | I can use it to be more sustainable | Should | 2 | Done | 8 | 26/01/2022 | 2022-04-01
21 | Eco-activist | suggest items to be added which will be put in a list and pend | the admin can accept it | Should | 2 | Done | 8 | 26/01/2022 | 31/01/2022
22 | Event Organisor | curate 'tours' of sustainable venues | I can make a plan to visit consecutive locations | Must | 3 | In Progress | 13 | 26/01/2022
23 | Hitchhiker | choose to go on a tour based on a goal | visit places based on a goal I'm interested in | Must | 3 | In Progress | 13 | 26/01/2022
24 | Member of the public | get most up to date data regarding recycling points displayed on a map | I can be more informed | Must | 3 | To Do | 13 | 2022-01-03
25 | Member of the public | save a webpage to my phone | I can access it easily | Must | 3 | To Do | 5 | 2022-01-02
26 | Mobile user | see a bigger map on the tours page | I can see it more easily | Must | 3 | To Do | 5 | 2022-04-02
27 | User | see a description of reasons to register to the website | I can be informed of the benefits of being a registered user | Must | 3 | To Do | 3 | 2022-04-02
28 | User | see padding between the icons on the home page | I can comfortably click on the correct one | Must | 3 | To Do | 1 | 2022-04-02