## Sheet1
AGILE PRODUCT BACKLOG
ID | As a(n)... | I want to be be able to... | So that... | Priority | Sprint | Status | Story Points | Date Added | Date Completed
1 | User | select 1 of the 17 goals | I can find out more information about it | Must | 1 | Done | 5 | 2022-01-24 | 2022-01-25
2 | User | see a list of items aligned with each goal | I can learn more about it | Must | 1 | Done | 3 | 2022-01-24 | 2022-01-25
3 | Admin | make edits to existing items and add new items | content can be updated if necessary | Must | 1 | Done | 8 | 2022-01-25 | 2022-01-27
4 | Admin | add users | they can add/remove/edit items | Must | 1 | Done | 23 | 2022-01-24 | 2022-01-27
4.1 | Admin | add users | they can make changes | Must | 1 | Done | 8 | 2022-01-24 | 2022-01-26
4.2 | User | add a new item(event/organisation) | more content can be added to the website | Must | 1 | Done | 4 | 2022-01-25 | 2022-01-27
4.3 | User | delete an item | any unnecessary content can be removed | Must | 1 | Done | 3 | 2022-01-25 | 2022-01-27
4.4 | User | edit an item | content can be updated if necessary | Must | 1 | Done | 8 | 2022-01-25 | 2022-01-27
5 | User | view items associated with a goal on a map | I can find them easily | Must | 1 | Done | 8 | 2022-01-24 | 2022-01-27
6 | User | have each item show more information about events including contacts | I can be more informed | Should | 1 | Done | 3 | 2022-01-24 | 2022-01-26
7 | User | view sustainable activities near my location | I can see what's on and get involved | Could | 1 | Done | 8 | 2022-01-24 | 2022-01-26
8 | User | see all UN guidance followed on branding | the UN is happy | Must | 2 | To Do | 5 | 2022-01-26
9 | User | use the app on my mobile device | it's accessible on the go | Must | 2 | To Do | 5 | 2022-01-24
10 | User | create a personal list of items | I can print it out to visit later | Should | 2 | To Do | 3 | 2022-01-24
11 | User | curate 'tours' of sustainable venues close together | more places can be visited | Should | 2 | To Do | 13 | 2022-01-26
12 | User | check into a location which will upload to a leaderboard amongst friends | I can compare my amount of check-ins with my friends' | Should | 2 | To Do | 20 | 2022-01-26
12.1 | User | check into an event through the website | I can see what places I have visited | Should | 2 | To Do | 7 | 2022-01-26
12.2 | User | upload to a leaderboard amongst friends | friends can see my amount of check-ins | Should | 2 | To Do | 13 | 2022-01-26 |  | a
13 | User | suggest items to be added which will be put in a list and pend | the admin can accept it | Could | 2 | To Do | 5 | 2022-01-26
14 | User | see data from the UN | I can use it to be more sustainable | Must | 3 | To Do | 3 | 2022-01-26
15 | User | check into a location through social media | I can share my experiences | Could | 3 | To Do | 8 | 2022-01-24