## Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | PRIORITY | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Setup website with database | 26 |  | HIGH | Completed
Setup SQL database | 5 | Matthew, Laura, Eddie |  |  | 3 | 2
Connect database to API | 13 | Matthew, Jamie, Euan |  |  | 8 | 5
Connect API to front-end | 8 | Jamie, Euan, Matthew |  |  | 4 | 4
As a user, I want to select 1 of the 17 sustainable development goals so that I could find out more information about it. | 5 |  | HIGH | Completed
List all sustainable goals in website | 2 | Jamie, Matthew |  |  | 2
Allow user to select a goal | 2 | Jamie, Euan |  |  | 2
Display goal information to user | 1 | Jamie |  |  | 1
As a user, I want to see a list of items aligned with each goal so I can learn more about it. | 3 |  | HIGH | Completed
Get website to list all items from API with text | 2 | Jamie, Matthew |  |  |  | 2
Get website to list all items from API with pictures | 1 | Matthew, Jamie, Euan |  |  |  | 1
As a user, I want to each item to show more information about the event so that I can be more informed. | 3 |  | HIGH | Completed
Get website to list all events from API with text | 3 | Euan, Jamie, Laura |  |  | 1 | 2
As an admin, I should be able to add users so they can add/edit/remove items | 8 |  | HIGH | Completed
Implement option to add users | 8 | Sem |  |  |  | 4 | 4
As a user (assigned by an admin), I want to be able to do alterations so that content can be updated. | 13 |  | HIGH | Completed
Allow users to add items | 5 | Sem |  |  |  | 3 | 2
Allow users to remove items | 3 | Sem |  |  |  | 3
Allow users to edit items | 5 | Sem |  |  |  | 2 | 2 | 1
As an admin, I wan to make edits to existing items and add new items, so that content can be updated if necessary | 8 |  | HIGH | Completed
Add new a new item/event | 5 | Sem |  |  |  | 5
Edit existing information about events/organisations | 3 | Sem |  |  |  |  | 3
As a user, I want to view items associated with a goal on a map so that I can find them easily. | 8 |  | HIGH | Completed
Connect Maps API to the site | 2 | Euan, Matthew, Jamie |  |  |  |  | 2
Add Icons for events based on location | 3 | Euan, Matthew, Jamie |  |  |  |  | 2 | 1
Link specific events to the page based on selected goalID | 3 | Euan, Matthew, Jamie |  |  |  |  | 2 | 1
As a user, I can view what sustainable activities are close to my location, so that I can see what is on and get involved | 8 |  | HIGH | Completed
Connect Maps API to the site | 1 | Euan, Jamie, Matthew |  |  |  |  | 1
Get users location | 4 | Matthew | [5 empty] | 4
Display events that are nearby users location | 3 | Matthew |  |  |  |  | 2 | 1
TOTAL | 82 |  |  |  | 21 | 33 | 20 | 8 | 0 | 0