## Sprint Backlog 2
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | PRIORITY | STATUS | DAY 0 | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a teen, I can use the app on my mobile device, so that it's accessible on the go | 1 |  | HIGH | Completed
Add approriate bootstrap commands | 1 | Matthew, Euan, Sem, Laura, Jamie, Eddie |  |  |  | 1
As an older person, I want the icons on the homepage to be bigger, so that I can immediately see what each item is. | 2 |  | HIGH | Completed
Make the image for each item bigger than the header text | 2 | Matthew |  |  |  | 2
As a colour-blind person, I want events on the map to be represented by sustainable dundee petals, so that I can differentiate between my location and event locations | 3 |  | HIGH | Completed
Change blue dots to sustainable dundee petals | 3 | Matthew |  |  |  | 3
As a member of the public, I should see the address of all events selected on the map, so that I could find the event easily | 5 |  | HIGH | Completed
Update database format | 1 | Sem |  |  |  |  | 1
Insert new data into database | 3 | Sem |  |  |  |  | 3
Add new data to map page | 1 | Sem |  |  |  |  | 1
As a user, I want to be able to register for the site so that I can use the site functionality. | 8 |  | HIGH | Completed
Add registration page | 4 | Sem |  |  |  |  | 4
Take away normal users' ability to edit items | 4 | Sem | [7 empty] | 4
As a member of the public, I want to be able to change my password so that my account is more secure. | 3 |  | HIGH | Completed
add change password page | 1 | Sem |  |  |  | 1
push the change to the database | 2 | Sem |  |  |  | 2
As a teen, I can check into a location through social media , so that I can share my experiences | 5 |  | HIGH | Completed
Add a button to check in (via social media) | 2 | Laura |  |  |  | 2
Generate a prepopulated tweet text | 3 | Laura |  |  |  |  | 3
As a teen, I want to be able to check in to a location through social media on the map, so that I don't need to go to a goal each time. | 2 |  | HIGH | Completed
able to check in on map | 2 | Sem | [6 empty] | 2
As a member of the public, I want to be able to see news about sustainability so that I could be more informed | 3 |  | HIGH | Completed
Integration with Sustainable Dundee twitter's page | 3 | Laura | [5 empty] | 3
As a teen, I should be able to check into a location through the website. | 8 |  | HIGH | Completed
Modify database to add check in counter | 3 | Sem | [6 empty] | 3
Add check in button to map events | 1 | Sem | [7 empty] | 1
Add check in button to single events page | 1 | Sem | [7 empty] | 1
display activity locations to a user | 1 | Matthew, Euan, Jamie |  |  |  | 1
let a user to check in into a specific event | 2 | Sem | [5 empty] | 2
As a teen, I should be able to check a leaderboard that shows how many events I have been to compared to my friends | 8 |  | HIGH | Completed
create leaderboard | 5 | Sem, Euan | [5 empty] | 5
go through the code to check if everything's compatible with the updated users table | 3 | Sem | [6 empty] | 3
As a teen, I should be able to add friends on the website after registering | 8 |  | HIGH | Completed
Add page to add friends on website | 4 | Euan, Jamie |  |  |  |  | 4
Implement notification feature for friend requests | 2 | Euan, Jamie |  |  |  |  | 2
Check if relationship already exists | 2 | Euan, Jamie |  |  |  |  | 2
As a teen, I should be able to see a friends list on the website | 5 |  | HIGH | Completed
Modify database to include friends | 2 | Sem |  |  |  |  | 2
Show friends on list | 3 | Euan, Jamie |  |  |  |  | 3
As an eco-activist, I want to be able to suggest things to be added to the list of events by putting into a holding thing so that it can be approved by admin and added to the website. | 8 |  | MEDIUM | Completed
Allow users to suggest events | 3 | Sem |  |  |  |  | 3
Add database table to hold suggested events | 2 | Sem |  |  |  |  | 2
Allow admin to approve or delete suggested events | 3 | Sem | [5 empty] | 3
As a member of the public, I can see data from the UN (i.e. dataset of recycling points in Dundee), so that I can use it to be more sustainable | 8 |  | MEDIUM | Completed
parsing data from online json file | 2 | Laura | [6 empty] | 2
adding recycling points on a map | 2 | Laura | [6 empty] | 2
adding appropriate markers | 2 | Laura | [7 empty] | 2
filtering points based on recycled items | 2 | Laura | [7 empty] | 2
As an event organiser, I want to have a ‘tour’ of sustainable venues shown on a map that are close together . | 8 |  | MEDIUM | Completed
Implement direction mapping | 5 | Matthew, Eddie | [7 empty] | 5
Add 'event organiser' users | 1 | Matthew, Eddie | [5 empty] | 1
Create tour database table | 2 | Matthew, Jamie, Eddie | [5 empty] | 2
TOTAL | 85 |  |  |  |  | 12 | 30 | 16 | 12 | 15 | 0
For burndown graph |  |  |  |  | 85 | 73 | 43 | 27 | 15 | 0 | 0